## Sheet1
See column descriptions in other tab
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points | Story Type
1 | As a student, I want to be able to see my tasks organized by importance so that I can stay organized. | 3 | High | D | 5 | F
2 | As a student, I want to be able to add an estimate of how long a task will take so that I can keep track of which tasks I should prioritize. | 4 | High | D | 3 | F
3 | As a student, I want to be able to see my work and class schedule so I can know when I will have time to do homework. |  | High | Backlog | 3 | F
4 | As a student, I want to be able to quickly see all of the tasks that I have due on a given day so that I can make sure I get everything done that I need to. |  | High | Backlog | 2 | F
5 | As a student, I want to be able to quickly see if I have any schedule conflicts between events so that I can know when I have conflicts. |  | Medium | Backlog | 2 | F
6 | As a business owner, I want my employees to have their work schedules visible separately so that they may easily identify when they need to work and I have more consistent employees. | 4 | High | IP | 3 | F
7 | As a parent, my family should be able to organize our busy schedules to see our most important events first so that we can attend events that are our highest priority. | 4 | Medium | IP | 2 | F
8 | As an athlete, I want my games and practices to be easily identifiable so that I can better organize my life and sports balance. |  | High | Backlog | 2 | F
9 | As a student, I want to be able to add tasks or scheduled events quickly and easily so that I can use my time efficiently. | 4 | Medium | IP | 3 | F
10 | As a user, I want to be able to organize my events by date, type, or priority so that I can quickly understand my schedule. |  | High | Backlog | 4 | F
11 | As a colorblind person, I would like the app to have a setting so that I can utilize the site’s color features to their fullest. | 4 | Medium | D | 4 | F
12 | As a student, I want to be able to see what I should be working on based on priority level, so that I can better organize my time. | 3 | High | D | 2 | F
13 | As a parent, I would like to be able to keep track of both my kids and my work schedule so I don’t miss any of their events. |  | Low | Backlog | 5 | F
14 | As a deaf person, I would appreciate having a vibration notification system so that I am still aware of notifications. |  | Medium | Backlog | 3 | F
15 | As a child, I would like the ability to link my calendar with my parents so we can coordinate schedules. |  | Low | Backlog | 5 | F
16 | Establish all user stories | 1+ | High | IP | 3 | KA
17 | Setup the GitHub and KanBan | 1+ | High | IP | 2 | T
18 | Create UI Mockups for testing and planning | 1+ | High | IP | 4 | T
19 | Create documentation | 1+ | High | IP | 8 | T

## Description of Columns
ID: unique # for each story * Story: Contains the user stories (one story per row) in priority order ▪ Formatted as “As a <user role>, I need to <feature needed> because of <benefit>. o Sprint: The story’s sprint number (when it gets implemented) o Priority: H (high), M (medium), L (low) o Status: Backlog, To Do, IP (in progress), QC (quality checking), D (done) o Estimate / Story Points: Number of story points gives an indication of the difficulty of the story’s development and testing as well as possibly an estimate of the number of hours to design, implement, and test the story.
The basic idea of story points is a story with 3 points is 3x the effort as a 1 point story, 2 points is 2x the effort, etc. In general without much experience it's hard for you to estimate relative feature sizes. Just do your best. Here's more information https://www.mountaingoatsoftware.com/blog/what-are-story-points