## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
Preliminary Requirements
19 | Create documentation | Revise Group HW 1 with feedback from TA | 1 | Finishing Deliverables 0 and 1 | KA | 1 | 1 | All 25%
16 | Establish all user stories | Revise User Stories From Deliverable 0 |  | Finishing Deliverables 0 and 1 |  | 1 | 1 | All 25%
19 | Create documentation | Revise Problem Statement from Deliverable 0 |  | Finishing Deliverables 0 and 1 |  | 1 | 1 | Jackson Hooper - 100%
|  | Create Product Backlog for Deliverable 1 |  | Finishing Deliverables 0 and 1 |  | 2 | 2 | Benjamin Tanguay - 100%
|  | Create Sprint Backlog for Deliverable 1 |  | Finishing Deliverables 0 and 1 |  | 2 | 2 | Jackson Hooper - 100%
|  | 15-30 Functional Requirments |  | Deliverable 1: Software Requirements Specifications |  | 2 | 2 | Marc Scully - 50% Jonathan Mathieu - 50%
|  | 10-15 Non-Functional Requirments |  | Deliverable 1: Software Requirements Specifications |  | 2 | 2 | Marc Scully - 50% Jonathan Mathieu - 50%
17 | Setup the GitHub and KanBan | Establish Build Environment - Push to Github |  | Deliverable 1 | T | 2 | 2 | Benjamin Tanguay - 70% Marc Scully - 10% Jonathan Mathieu - 10% Jackson Hooper - 10%
19 | Create documentation | Sprint Review |  | Deliverable 1 | KA | 2 | 2 | All 25%
|  | Peer-Review Report |  | Deliverable 1 |  | 1 | 1 | All 25%
Deliverable 2
19 | Create documentation | Update SRS Document | 2 | Deliverable 2 | KA | 3 | 3 | Marc Scully - 50% Jonathan Mathieu - 50%
|  | Update Product Backlog |  | Deliverable 2 |  | 1 | 1 | Ben Tanguay - 100%
|  | Update Sprint Backlog |  | Deliverable 2 |  | 1 | 1 | Jackson Hooper - 100%
17 | Setup the GitHub and KanBan | Commit to Github: All members must commit something |  | Deliverable 2 | T | 1 | 1 | All 25%
|  | Update KanBan / Add Tasks |  | Deliverable 2 | KA | 2 | 2 | Ben Tanguay - 100%
19 | Create documentation | Sprint Review 2 |  | Deliverable 2 |  | 2 | 2 | All 25%
18 | Create UI Mockups for testing and planning | Usability Testing Paper Prototype and Script |  | Deliverable 2 |  | 2 | 2 | Ben Tanguay - 50% Jonathon Mathieu - 50%
19 | Create documentation | Architecture Design |  | Deliverable 2 |  | 1 | 1 | Jonathon Mathieu - 100%
|  | Use Case Diagrams/Models and Descriptions |  | Deliverable 2 |  | 2 | 2 | Ben Tanguay - 100%
17 | Setup the GitHub and KanBan | New implementation of project onto Github |  | Deliverable 2 | T | 2 | 2 | Jackson Hooper - 75% Benjamin Tanguay - 25%
Deliverable 3
19 | Create documentation | Create Domain Model | 3 | Deliverable 3 | T | 2 | 2 | Jonathon Mathieu - 100%
18 | Create UI Mockups for testing and planning | Review/Update Usability Testing Script |  | Deliverable 3 | KA | 1 | 1 | Marc Scully - 50% Jonathan Mathieu - 50%
18 | Do usability testing | Review/Update Usability Testing Script |  | Deliverable 3 |  | 2 | 2 | Marc Scully - 50% Jonathan Mathieu - 50%
19 | Create documentation | Review/Update Arcatecture Design |  | Deliverable 3 |  | 1 | 1 | Jonathan Mathieu - 100%
|  | Update Product Backlog |  | Deliverable 3 |  | 1 | 1 | Benjamin Tanguay - 100%
|  | Update Sprint Backlog |  | Deliverable 3 |  | 1 | 1 | Jackson Hooper - 50% Benjamin Tanguay - 50%
17 | Setup the GitHub and KanBan | Commit to Github: All members must commit something |  | Deliverable 3 | T | 2 | 2 | All 25%
|  | Update KanBan / Add Tasks |  | Deliverable 3 |  | 1 | 1 | Benjamin Tanguay - 100%
19 | Create documentation | Sprint Review 3 |  | Deliverable 3 |  | 1 | 1 | All 25%
1 | As a student, I want to be able to see my tasks organized by importance so that I can stay organized. | Create task organization |  | Deliverable 3 | F | 3 | 3 | Jackson Hooper - 100%
12 | As a student, I want to be able to see what I should be working on based on priority level, so that I can better organize my time. | Add priority functionality |  | Deliverable 3 |  | 2 | 2 | Jackson Hooper - 100%
17 | Setup the GitHub and KanBan | New implementation of project onto Github |  | Deliverable 3 |  | 3 | 3 | Jackson Hooper - 50% Marc Scully - 50%
|  | Impliment Continous Integration |  | Deliverable 3 |  | 3 | 3 | Marc Scully - 100%
Deliverable 4
2 | As a student, I want to be able to add an estimate of how long a task will take so that I can keep track of which tasks I should prioritize. | Add task length priority | 4 | Deliverable 4 | F | 3 | 3 | Jackson Hooper - 100%
19 | Create documentation | Create Detalied Technical Design |  | Deliverable 4 | T | 3 | 3 | Jonathon Mathieu - 100%
17 | Setup the GitHub and KanBan | Update Kanban / Add Tasks |  | Deliverable 4 |  | 1 | 1 | Benjamin Tanguay - 100%
|  | Commit to Github: All members must commit something |  | Deliverable 4 |  | 1 | 1 | All 25%
19 | Create documentation | Update Product Backlog |  | Deliverable 4 |  | 1 | 1 | Benjamin Tanguay - 100%
|  | Update Sprint Backlog |  | Deliverable 4 |  | 1 | 1 | Benjamin Tanguay - 100%
|  | Review feedback from deliverable 2 and fix mistakes |  | Deliverable 4 |  | 4 | 4 | Marc Scully - 25% Benjamin Tanguay - 75%
|  | Sprint Review 4 |  | Deliverable 4 |  | 1 | 1 | All 25%
6 | As a business owner, I want my employees to have their work schedules visible separately so that they may easily identify when they need to work and I have more consistent employees. | Add priority to tasks |  | Deliverable 4 | F | 3 | 3 | Jackson Hooper - 100%
7 | As a parent, my family should be able to organize our busy schedules to see our most important events first so that we can attend events that are our highest priority. | Add priority to tasks |  | Deliverable 4 |  | 2 | 2 | Marc Scully - 100%
9 | As a student, I want to be able to add tasks or scheduled events quickly and easily so that I can use my time efficiently. | Easily be able to add and edit tasks |  | Deliverable 4 |  | 3 | 3 | Jackson Hooper - 100%
11 | As a colorblind person, I would like the app to have a setting so that I can utilize the site’s color features to their fullest. | Add colorblind setting |  | Deliverable 4 |  | 4 | 4 | Jackson Hooper - 100%

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657